# Riverside Expansion Brief

Prepared for the September operations launch

The Riverside pilot opens on September 14. Field teams need a one-page brief that links readers to the program portal and lets them jump directly to the Risks section.

Program portal | Jump to Risks

## Overview

The site will support the first wave of evening fulfillment volume for the east corridor.

Managers should review the launch window, staffing checkpoints, and known constraints before September 14.

## Milestones

Vendor onboarding closes August 12.

Site readiness review is August 26.

Final staffing confirmations are due September 2.

## Risks

Badge printing can slip if headcount changes after August 20.

The loading dock remains shared with the warehouse until September 7.

## Appendix Resources

Escalation desk: ops@example.com

Program portal: https://example.com/program-portal